Гуманитарный проект

«Ты не одинок»

| 1. Наименование проекта: «Ты не одинок» |  |
| --- | --- |
| 2. Срок реализации проекта: 2026-2027 |  |
| 3. Организация – заявитель, предлагающая проект: государственное учреждение «Территориальный центр социального обслуживания населения Партизанского района г. Минска» |  |
| 4. Целевая группа: лица, оказавшиеся в трудной жизненной ситуации; лица, освободившиеся из учреждений уголовно-исполнительной системы; лица без определенного места жительства. |  |
| 5. Актуальность проекта: Проблема бездомности является наиболее актуальной на данный момент в нашем обществе. Бездомным людям требуется длительная социально-трудовая реабилитация. Граждане, которые были временно изолированы от общества, возвращаются уже, как правило, в новые изменившиеся социально-экономические условия. Для многих новые условия жизни из-за снижения адаптационных способностей и возможностей становятся непреодолимыми. Все это затрудняет процесс ресоциализации в открытом социуме либо ведет к росту новых преступных деяний. Пребывание лиц в местах лишения свободы, проживание лиц без определенного места жительства на улице сказывается и на индивидуальных социально-психологических и личностных особенностях человека. Почти каждый данной категории нуждается в информационно-консультационной, психологической поддержке, восстановлению документов, помощи в трудоустройстве, медицинской и юридической помощи, восстановлению семейных и коммуникативных связей. |  |
| 6. Цель проекта: Профилактика асоциальных проявлений, снижение правонарушений, улучшение эпидемиологической обстановки на территории города Минска. |  |
| 7. Задачи: проведение информационных мероприятий в системе профилактики на базе центра; создание дополнительных возможностей для получения различной помощи гражданам; психологическая поддержка граждан; возвращение граждан к нормальной жизнедеятельности, создание прочных стереотипов социально-положительного поведения. |  |
| 8. Краткое описание мероприятий в рамках проекта: изготовление брошюр «О социальной адаптации лиц, оказавшихся в трудной жизненной ситуации»; содействие в восстановлении утраченных документов: оплата госпошлины, оплата за фото услуги; оплата справки РУП «МГА по государственной регистрации и земельному кадастру»; оплата за регистрацию по месту жительства/пребывания; содействие в получении средств гигиены и ухода; содействие в получении продуктовых наборов. |  |
| 9. Ожидаемые результаты: возвращение лиц, оказавшихся в трудной жизненной ситуации, лиц, освободившихся из учреждений уголовно-исполнительной системы; лиц без определенного места жительства к самостоятельной жизни в социуме; повышение коммуникативного потенциала, умение защищать свои интересы и самостоятельно решать жизненные проблемы; снижение стигматизации со стороны общества к целевым группам проекта. |  |
| 10. Дальнейшая деятельность по окончании проекта: оказание социального сопровождения, помощи в трудоустройстве целевым группам проекта; популяризация деятельности по реализации проекта в социальных сетях. |  |
| 9. Общий объем финансирования (в долларах США): |  |
| Источник финансирования | Объем финансирования (в долларах США) |
| Средства донора: |  |
| оплата госпошлины, оплата за фото услуги | 250 USD |
| оплата за регистрацию по месту жительства/пребывания | 150 USD |
| оплата справки РУП «МГА по государственной регистрации и земельному кадастру» | 150 USD |
| оплата средств гигиены и ухода | 70 USD |
| оплата продуктовых наборов | 100 USD |
| Закупка инвентаря и оборудования: |  |
| Компьютер | 720 USD |
| МФУ | 300 USD |
| Учебные материалы: |  |
| Визуальные пособия | 30 USD |
| Средства гигиены: |  |
| Дезинфицирующие средства | 40 USD |
| Маски защитные одноразовые | 20 USD |
| Итого: | 1830 USD |
| 10. Место реализации проекта (область/район, город): г. Минск, пер. Клумова, 3 |  |
| 11. Контактное лицо: инициалы, фамилия, должность, телефон, адрес электронной почты Кленицкая Ирина Николаевна, заведующий отделением дневного пребывания для граждан пожилого возраста +375-44-752-41-69, 8017 272 99 61 ktrud.tccon.part@minsk.gov.by |  |

| Humanitarian project "You're not alone" 1. Name of the project: "You are not alone" |  |
| --- | --- |
| 2. Project implementation period: 2026-2027 |  |
| 3. Applicant organization proposing the project: State Institution "Territorial Center for Social Services for the Population of the Partizansky District of Minsk" |  |
| 4. Target group: persons in difficult life situations, persons released from institutions of the penitentiary system; persons without a fixed place of residence. |  |
| 5. Relevance of the project: The problem of homelessness is the most urgent at the moment in our society. Homeless people need long-term social and labor rehabilitation. Citizens who were temporarily isolated from society are already returning, as a rule, to new changed socio-economic conditions. For many, new living conditions become insurmountable due to a decrease in adaptive abilities and opportunities. All this complicates the process of resocialization in an open society or leads to an increase in new criminal acts. The stay of persons in places of deprivation of liberty, the residence of persons without a fixed place of residence on the street also affects the individual socio-psychological and personal characteristics of a person. Almost everyone in this category needs information and consulting, psychological support, restoration of documents, assistance in employment, medical and legal assistance, restoration of family and communication ties. |  |
| 6. Project goal: Prevention of antisocial manifestations, reduction of offenses, improvement of the epidemiological situation in the city of Minsk. |  |
| 7. Tasks: - conducting information activities in the prevention system on the basis of the center; - creation of additional opportunities for citizens to receive various assistance; - psychological support for citizens; - the return of citizens to normal life, the creation of strong stereotypes of socially positive behavior. |  |
| 8. Brief description of the project activities: -production of brochures "On the social adaptation of persons in difficult life situations"; - assistance in the restoration of lost documents: payment of state duty, payment for photo services; - payment for a certificate from the RUE "MGA for State Registration and Land Cadastre"; - payment for registration at the place of residence/stay; - assistance in obtaining hygiene and care products; - assistance in obtaining food packages. |  |
| 9. Expected results: - the return of persons in difficult life situations, persons released from institutions of the penal correction system; persons without a fixed place of residence to an independent life in society; - increasing communication potential, the ability to protect one's interests and independently solve life problems; - reducing stigmatization by society towards the target groups of the project. |  |
| 10. Follow-up activities after the end of the project: return of persons in difficult life situations, persons released from institutions of the penal correction system; persons without a fixed place of residence to an independent life in society; increasing communication potential, the ability to protect one's interests and independently solve life problems; reducing stigmatization by society towards the target groups of the project. |  |
| 9. Общий объем финансирования (в долларах США): |  |
| Source of funding | Funding (in United States dollars) |
| Donor funds: |  |
| payment of state duty, payment for photo services | 250 USD |
| Payment for registration at the place of residence/stay | 150 USD |
| payment for a certificate from the RUE "MGA for State Registration and Land Cadastre" | 150 USD |
| Payment for hygiene and care products | 70 USD |
| Payment for food packages | 100 USD |
| Purchase of inventory and equipment: |  |
| Computer | 720 USD |
| MFPs | 300 USD |
| Study materials: |  |
| Visual aids | 30 USD |
| Hygiene products: |  |
| Disinfectants | 40 USD |
| Disposable protective masks | 20 USD |
| Total: | 1830 USD |
| 10. Project location (region/district, city): Minsk, Klumova Lane, 3 |  |
| 11. Contact: initials, surname, position, phone, e-mail address Klenitskaya Irina Nikolaevna, Head of the Day Care Department for Elderly Citizens +375-44-752-41-69, 8017 272 99 61 ktrud.tccon.part@minsk.gov.by |  |